## Sheet1
Milestones
Milestone Number | Milestone Description | Continuation Criteria
1 | Prototype A: Basic Combat possible. Player can run around with draft animation and attack with draft animation. The attack will interact with the enemy, who will be stationary and will play draft animation upon health depletion. Player will run around a very basic terrain, ie. mostly flat with some boundaries. A sound effect will play when player attacks and enemy dies. No UI required. No Networking required. No Main Menu required. No Respawn required. No Equiment or Skill system required. | - 2 Draft Models with Basic textures (Enemy and Player) - 3 Animations (Walk, Attack, Death) - Basic Input System (Player Movement, Player Basic Attack) - Basic Stats System (Enemy Health, Player Attributes) - Basic Combat System (Player can damage Enemy with attack) - Basic Terrain (Player can move around and hit boundaries)
2 | Prototype B: Player can attack enemies using a basic skill system. Player can examine a predetermined equipement set. Player can pickup an item off the ground. Enemies move and attack player. Basic UI required showing health, skills, and equipment. No Networking required. No Main Menu required. No Respawn required. | - An basic Animation for each skill - Enemy Attack animation - Enemy AI and Pathing - Basic Item model - Equipment and Item inteface - Combat UI - Input interface to interact with item on ground
3 | Prototype C: