## Sheet1
Game System Tasks
Component: | RPG Systems
Description: | Implementation of all RPG elements such as Combat, Skill Trees, Equipment and Item Systems.
Task | Subtask | Description | Requirements
1
2
3
Component: | Dynamic Systems and AI
Description: | Implementation of dynamic systems such as Dynamic Assault System. Implementation of the Combat Enemy AI and Supporting Character AI.
Task | Subtask | Description | Requirements
1 |  | Investigate and Implement C# Statemachine Templates
2 |  | Investigate and Implement Prototype code system in Unity
3 | 0 | Prototype Dynamic Assault System
| 1 | Design state machine for Dynamic Assault System
| 2 | Build Dynamic Assault System Prototype, using text output for verification
4 | 0 | Prototype Enemy/Supporting Character AI | Level with Character or Enemy Model
| 1 | Prototype Aggro state machine | Level with Character or Enemy Model
| 2 | Prototype Pathing System | Level with Character or Enemy Model
| 3 | Prototype Attack and Animation Controls System | Character or Enemy Model
5 |  | Implement Enemy/Supporting Character AI | Pre-Alpha System
6 |  | Implement Dynamic Assault Sysetm | Pre-Alpha System
Component: | Networking
Description: | Implementation of Online Coop and Account Login on the Server, and Client.
Task | Subtask | Description | Requirements
1 |  | Determine proper coding language for Server
2 |  | Setup Server infrastructure
3 |  | Design Login requirements and connection Protocol
4 |  | Design Matchmaking and Lobby requirements and communication Protocol
5 |  | Develop simple Login and Matchmaking test Client
6 |  | Implement Login and user database on Server
7 |  | Implement Matchmaking and Lobby on Server
8 |  | Test Login and Matchmaking Server
9 |  | Implement Login and Matchmaking in Client code | Pre-Alpha Build
10 |  | Design Coop data protocol | Pre-Alpha Build
11 |  | Implement Coop data protocol | Pre-Alpha Build
Component: | Physics
Description: | Analysis and Implementation of all Physic-related features and components of Terrain, Characters and Pickupables.
Task | Subtask | Description | Requirements
1 |  | Determine what components benefit from Physics | Basic Level Designed and Assets available
2 |  | Investigate the usage of physics on Player weapons | Basic Character Model with Weapon available with Scenery Assets available
3 |  | Implement Phyics using Unity Editor on required components | 1,2